## Sheet1
Organization: EdgyCraft |  | Name: Static_Code_Checker |  |  |  | ID No: (Enter Project or Time Tracking Number, etc) |  |  |  | Estimate Valid For: 4 weeks
Static_Code_Checker |  | Purpose: Estimate the amount of time sent on the project
Estimator: All |  | Authorizer: Jake Gadaleta
Date Required By: 2/24/2020 |  | Requestor: Dr. Pranshu Gupta
Completion Date: 4/4/2020 |  | Requested Date: N/A
Work Estimation Details |  | Optimistic | Most Likely | Pessimistic | Confidence | 75% | 85% | 95% | 99.5% | Supporting Document Links: (Enter Links to Requirements, Specifications, or other supporting documents in this column)
SDLC Phases | Activity/Task (Requirement number) | Effort Hrs | Effort Hrs | Effort Hrs | Factor | Confidence | Confidence | Confidence | Confidence
Initiation/Administration
| Status Meetings | 0.5 | 0.5 | 2 | 0.25 | 0.75 | 1 | 1.25 | 1.5
| Status Reporting | 0.5 | 0.5 | 2 | 0.25 | 0.75 | 1 | 1.25 | 1.5
Planning
| Requirements/Scope Review | 0.5 | 0.5 | 1 | 0.083333 | 0.58333 | 0.66667 | 0.75 | 0.83333
| Resource Requirements Review | 0.5 | 0.5 | 1 | 0.083333 | 0.58333 | 0.66667 | 0.75 | 0.83333
| Assumptions and Constraints Specification | 0.5 | 0.5 | 1 | 0.083333 | 0.58333 | 0.66667 | 0.75 | 0.83333
Analysis
| Functional Impact Analysis | 0.5 | 0.5 | 1 | 0.083333 | 0.58333 | 0.66667 | 0.75 | 0.83333
| Functional Requirements Specification | 0.5 | 0.5 | 1 | 0.083333 | 0.58333 | 0.66667 | 0.75 | 0.83333
| Use Case Development |  |  |  | 0 | 0 | 0 | 0 | 0
| Test Plan Specification |  |  |  | 0 | 0 | 0 | 0 | 0
| Architectural Requirements Specification |  |  |  | 0 | 0 | 0 | 0 | 0
| Security Requirements Specification |  |  |  | 0 | 0 | 0 | 0 | 0
| Application Impact Analysis | 0.5 | 0.5 | 1 | 0.083333 | 0.58333 | 0.66667 | 0.75 | 0.83333
| Risk Analysis |  |  |  | 0 | 0 | 0 | 0 | 0
Design
| Technical Design Development | 0.5 | 0.5 | 1 | 0.083333 | 0.58333 | 0.66667 | 0.75 | 0.83333
| Prototype Presentation | 0.5 | 0.5 | 1 | 0.083333 | 0.58333 | 0.66667 | 0.75 | 0.83333
| Design Acceptance | 0.5 | 0.5 | 1 | 0.083333 | 0.58333 | 0.66667 | 0.75 | 0.83333
Construction
| Coding | 4 | 6 | 8 | 0.66667 | 6 | 6.6667 | 7.3333 | 8
| Unit Testing | 2 | 3 | 4 | 0.33333 | 3 | 3.3333 | 3.6667 | 4
| Test Plan Updates | 1 | 2 | 3 | 0.33333 | 2 | 2.3333 | 2.6667 | 3
| Test Data Validation | 1 | 2 | 3 | 0.33333 | 2 | 2.3333 | 2.6667 | 3
| Software Configuration Management | 3 | 4 | 5 | 0.33333 | 4 | 4.3333 | 4.6667 | 5
| Release/Build Updates | 2 | 3 | 4 | 0.33333 | 3 | 3.3333 | 3.6667 | 4
| User Documentation | 2 | 4 | 6 | 0.66667 | 4 | 4.6667 | 5.3333 | 6
Testing
| Test Plan Finalization | 1 | 2 | 3 | 0.33333 | 2 | 2.3333 | 2.6667 | 3
| Documentation Validation | 1 | 2 | 3 | 0.33333 | 2 | 2.3333 | 2.6667 | 3
| Integration Testing | 2 | 3 | 5 | 0.5 | 3.1667 | 3.6667 | 4.1667 | 4.6667
| Performance Testing |  |  |  | 0 | 0 | 0 | 0 | 0
Implementation
| Final Documentation Review | 3 | 4 | 5 | 0.33333 | 4 | 4.3333 | 4.6667 | 5
| Internal Staff Training | 2 | 2 | 2 | 0 | 2 | 2 | 2 | 2
Work Estimate Totals |  | 29.5 | 42.5 | 64 |  | 43.9167 | 49.6667 | 55.4167 | 61.1667
Estimate Assumptions: | (Enter Assumptions here and number them)
Estimate Constraints: | (Enter Constraints here and number them)
Estimate Risks: | (Enter Risks here and number them)
Notes: | (Enter Special Instructions, Notes, etc here)